## Sheet1
TASK 1 | START DATE | DAYS TO COMPLETE
Requirements | 2019-10-14 | 2
Synopsis | 2019-10-16 | 7
Design | 2019-10-16 | 7
Database creation | 2019-11-13 | 17
Java connectivity | 2019-12-02 | 20
Mongo DB queries | 2019-12-22 | 16
Improvements and report | 2020-01-08 | 15